## Feuille 1
| Tasks | Not started | In Progress | Done | Assigned to
As a researcher, I would like to add tags to quotes from the transcript of my zoom meeting so that I can analyze the data that I got from the meeting easier | Implement the front end/ UI (html, css, javascript) |  |  |  | Abdulmalik
| Import transcripts |  |  |  | Brenyn
| Add tags to transcript |  |  |  | Abdulmalik
Create Relationships between tags/ themes
| Save Transcript |  |  |  | Brenyn
As a user, I will be able to log in so that I am redirected to the appropriate pages | Create Roles |  |  |  | Vivien
| Add the roles to session variables |  |  |  | Gerard
| Redirect unauthorised users to the right URL |  |  |  | Gerard
As a researcher, I would like to be able to add multiple choice questions as well as open ended questions to my questionnaire | Add multiple choice option to the creation of survey |  |  |  | Dominic
| add multiple choice to the completion of a survey |  |  |  | Justas
As a phD student, I would like to be able to fill in my ethics forms online and submit it so that I can go through this process quick without the hassle | Create checklists |  |  |  | Dominic
| Add styling |  |  |  | Mark
| Create Ethics Froms |  |  |  | Dominic
As a researcher, I should be able to keep track of which users have completed which questionnaires so that I can invite them to complete another in the future | Create table that displays the completed questionaires and users |  |  |  | Justas
| create a way to filter the table |  |  |  | Justas
As a participant, I should be shown my answers to a survey after completing it so that I can check my answers. | Create form that shows the answers and questions that the user typed |  |  |  | Justas
As a user I would like to sign up as a participant or researcher | Create sign up page with username, password and role input fields |  |  |  | Gerard
| Hash passwords before storing into database |  |  |  | Gerard