## Sheet1
User Stories | Story Points | Priority | Status | Sprint
As a researcher, I would like to be able to create my own questionnaire so that I do research | 13 | High | Complete | 1
As a researcher, I should be able to keep track of which users have completed which questionnaires so that I can invite them to complete another in the future | 8 | Medium | Completed | 2
As a researcher, I would like the ability to send my questionnaires out so that users could take it | 5 | High | Complete | 1
As a researcher, I would like to be able to export the data from the answered questionnaires so that I can put it in different softwares for analysis | 3 | High | Complete | 1
As a researcher, I would like to be able to visualize the data so that I can analyse it | 13 | High | In progress | 1
As a researcher, I would like to add tags to quotes from the transcript of my zoom meeting so that I can analyze the data that I got from the meeting easier | 13 | Medium | In progress | 1,2
As a researcher, I would like add multiple tags to one quote so that I could organize them better | ? | Medium | To Do
As a researcher, I would like to add multiple quotes to one theme so that I could organize them better | ? | Medium | To Do
As a researcher, I would like to generate relationships between quotes so that I could group them together | ? | Medium | To Do
As a researcher, I would like to be able to set up video calls and screen sharing with my users so that it would be easier to set up planned work | ∞ | Low | To Do
As a user, I would like to have different roles assigned to me so that I could use the system for how it’s intended for me | 5 | High | Completed | 2
As a phD student, I would like to be able to fill in my ethics forms online and submit it so that I can go through this process quick without the hassle | 8 | Medium | In Progress | 2
As a phD student, I would like to receive a feedback for submission so that i’m sure that my filled-in forms got sent successfully | 5 | Medium | To Do
As a phD student, I would like to receive notifications of my forms approval so that I can carry out my experiment as soon as possible | 5 | Medium | To Do
As a phD student, I would like to have a central control system that collects all the data from other systems i use so that it would be easier to manage | ∞ | Low | To Do
As a phD student, I would like to sync up my research cameras automatically so that I could save time | ? | Low | To Do
As a participant, I would like to access questionnaires so that I can answer them | 13 | High | Complete | 1
As a researcher, I would like to be able to add multiple choice questions as well as open ended questions to my questionnaire | 8 | High | Complete | 2
As a user, I will be able to log in so that I am redirected to the appropriate pages | 8 | High | Complete | 2
As a user, I will be able to sign up so that I can log in and use the website | 5 | High | Complete | 2
As a participant, I should be shown my answers to a survey after completing it so that I can check my answers. | 3 | Medium | Complete | 2